Submitted To:

Sri Chaitanya School Coimbatore -1

Tamil Nadu

Wizklub Futurz Program

Weekly Progress Report

Report Date: 20-Feb-2023

Wizklub Futurz Program - Progress Report Program Start Date: 17-Oct-2022

Trainer: Kalai Selvan

Report for: 13-Feb-2023 to 18-Feb-2023 Session Completion Status:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Slot-1** | | | | | | |
| **Date** | **Grade** | **Batch** | **No. of Sessions Planned** | **No. of Sessions Conducted** | **Name of the Session** | **No. of Sessions canceled** |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 14-Feb-2023 | 6 | Batch 1 | 1 | 1 | Technathon 2023 | 0 |
| 15-Feb-2023 | 5 | Batch 1 | 1 | 1 | Technathon 2023 | 0 |
| 15-Feb-2023 | 4 | Batch 1 | 1 | 1 | Technathon 2023 | 0 |
| 15-Feb-2023 | 7 | Batch 1 | 1 | 1 | Technathon 2023 | 0 |
| 15-Feb-2023 | 5 | Batch 2 | 1 | 1 | Technathon 2023 | 0 |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Slot-2** | | | | | | |
| **Date** | **Grade** | **Batch** | **No. of Sessions Planned** | **No. of Sessions Conducted** | **Name of the Session** | **No. of Sessions canceled** |
| 15-Feb-2023 | 4 | Batch 4 | 1 | 1 | Main Idea Stated | 0 |
| 15-Feb-2023 | 3 | Batch 3 | 1 | 1 | Main Idea Stated | 0 |
| 16-Feb-2023 | 3 | Batch 1 | 1 | 1 | Cause and Effect-Skill Workouts | 0 |
| 16-Feb-2023 | 5 | Batch 2 | 1 | 1 | Cause and Effect-Skill Workouts | 0 |
| 16-Feb-2023 | 4 | Batch 2 | 1 | 0 | Main Idea Stated | 1 |
| 16-Feb-2023 | 4 | Batch 3 | 1 | 1 | Main Idea Stated | 0 |
| 16-Feb-2023 | 8 | Batch 1 | 1 | 1 | WizGear: LED Strip | 0 |
| 17-Feb-2023 | 5 | Batch 1 | 1 | 1 | Main Idea Stated | 0 |
| 17-Feb-2023 | 3 | Batch 2 | 1 | 1 | Cause and Effect-Skill Workouts | 0 |
| 17-Feb-2023 | 5 | Batch 3 | 1 | 1 | Main Idea Stated | 0 |
| 17-Feb-2023 | 4 | Batch 1 | 1 | 1 | Main Idea Stated | 0 |
| 17-Feb-2023 | 6 | Batch 1 | 1 | 1 | HOTS Review | 0 |
| 17-Feb-2023 | 7 | Batch 1 | 1 | 1 | Wiz SKill: Intro to Conversation AI | 0 |

Attendance Status:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Slot-1** | | | | | | | |
| **Date** | **Grade** | **Batch** | **Total No. of students** | **Name of the Session** | **No. of Present** | **No. of Absent** | **Attendanc e %** |
| 13-Feb-2023 | 3 | Batch 1 | 26 | Technathon 2023 | 24 | 2 | 92 |
| 13-Feb-2023 | 5 | Batch 2 | 24 | Technathon 2023 | 21 | 3 | 88 |
| 13-Feb-2023 | 4 | Batch 2 | 21 | Technathon 2023 | 20 | 1 | 95 |
| 13-Feb-2023 | 4 | Batch 3 | 12 | Technathon 2023 | 9 | 3 | 75 |
| 13-Feb-2023 | 8 | Batch 1 | 11 | Technathon 2023 | 10 | 1 | 91 |
| 14-Feb-2023 | 3 | Batch 3 | 23 | Technathon 2023 | 22 | 1 | 96 |
| 14-Feb-2023 | 3 | Batch 2 | 24 | Technathon 2023 | 23 | 1 | 96 |
| 14-Feb-2023 | 5 | Batch 3 | 21 | Technathon 2023 | 20 | 1 | 95 |
| 14-Feb-2023 | 4 | Batch 4 | 18 | Technathon 2023 | 16 | 2 | 89 |
| 14-Feb-2023 | 6 | Batch 1 | 8 | Technathon 2023 | 6 | 2 | 75 |
| 15-Feb-2023 | 5 | Batch 1 | 14 | Technathon 2023 | 11 | 3 | 79 |
| 15-Feb-2023 | 4 | Batch 1 | 20 | Technathon 2023 | 20 | 0 | 100 |
| 15-Feb-2023 | 7 | Batch 1 | 8 | Technathon 2023 | 6 | 2 | 75 |
| 15-Feb-2023 | 5 | Batch 2 | 24 | Technathon 2023 | 21 | 3 | 88 |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Slot-2** | | | | | | | |
| **Date** | **Grade** | **Batch** | **Total No. of students** | **Name of the Session** | **No. of Present** | **No. of Absent** | **Attendance**  **%** |
| 15-Feb-2023 | 4 | Batch 4 | 18 | Main Idea Stated | 15 | 3 | 83 |
| 15-Feb-2023 | 3 | Batch 3 | 23 | Main Idea Stated | 11 | 1 | 92 |
| 16-Feb-2023 | 3 | Batch 1 | 26 | Cause and Effect-Skill Workouts | 25 | 1 | 96 |
| 16-Feb-2023 | 5 | Batch 2 | 24 | Cause and Effect-Skill Workouts | 22 | 2 | 92 |
| 16-Feb-2023 | 4 | Batch 2 | 21 | Main Idea Stated | 0 | 0 | 0 |
| 16-Feb-2023 | 4 | Batch 3 | 12 | Main Idea Stated | 11 | 1 | 92 |
| 16-Feb-2023 | 8 | Batch 1 | 11 | WizGear: LED Strip | 10 | 1 | 91 |
| 17-Feb-2023 | 5 | Batch 1 | 14 | Main Idea Stated | 12 | 2 | 86 |
| 17-Feb-2023 | 3 | Batch 2 | 24 | Cause and Effect-Skill Workouts | 20 | 4 | 83 |
| 17-Feb-2023 | 5 | Batch 3 | 21 | Main Idea Stated | 16 | 5 | 76 |
| 17-Feb-2023 | 4 | Batch 1 | 20 | Main Idea Stated | 20 | 0 | 100 |
| 17-Feb-2023 | 6 | Batch 1 | 8 | HOTS Review | 5 | 3 | 63 |
| 17-Feb-2023 | 7 | Batch 1 | 8 | Wiz SKill: Intro to Conversation AI | 6 | 2 | 75 |

Deviation Report:

* Due to the power shut down on 16th Feb, the session was rescheduled for grade 4.

Program Session Schedule and Session Description:

|  |  |  |  |
| --- | --- | --- | --- |
| **Session** | **Module** | **Session Name** | **Session Description** |
| S20 | HOTS | Main Idea Stated | Main idea of an article is its central thought, or the most important point the author is trying to make. It helps us summarize and understand the key idea in any article. Main Idea Stated helps in language/ comprehension skills. Children learn how to extract central thought from a text or a story. |
| S18 | HOTS | Cause and Effect-Skill Workouts | Students solve questions of this skill on the Wizklub app. This gives them a deeper understanding of skill application. |
| S17 | YPDP | WizGear: LED Strip | In this session, students learned about the WizGear LED Strip, which is a key component of the WizIoT Smart Light. They also learned how to program the individual LEDs on the strip to display different lighting effects. This may have involved using the concept of colour formation, which is the combination of different colours to create the desired effect. The students may have also reviewed the concept of conditional statements and their use in programming. |
| S19 | HOTS | HOTS Review | Revision of all the skills taught so far. |
| S20 | YPDP | Wiz SKill: Intro to Conversation AI | This session has introduced students to the basics of conversational AI and Artiﬁcial Intelligence. Students learnt about Alexa and Alexa-enabled devices and had their ﬁrst conversation with Alexa. |
| Technathon |  | Technathon | This competition is designed to challenge and excite kids aged 6-14 with a variety of coding challenges. This competition includes simulation-based, IoT hardware-based, and machine learning-based programming challenges. All of the challenges are designed to be fun and engaging, while also encouraging kids to use their creativity and problem-solving skills. |